## 4th qtr
20% COMPONENT OF THE IRA UTILIZATION
As of 0ctober 31, 2021
Province, City or Municipality : BROOKE'S POINT, PALAWAN
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
1 | Construction of Barangay Health Station | Brgy. Aribungos, Brooke's Point, Palawan | 2200000 | 6/24/2021 | 11/30/2021 | 65% | 1910164.52 |  | On-going
2 | Construction of Barangay Health Station | Brgy. Barong Barong, Brooke's Point, Palawan | 2200000 | 8/22/2021 | 2021-08-02 | 55% | 2167994.52 |  | On-going
3 | Construction of Barangay Health Station | Brgy. Saraza, Brooke's Point, Palawan | 2200000 | 10/20/2021 | 4/30/2021 | 10% | 1795431.42 |  | On-going
4 | Proposed Drainage System with RCPC Installation | Ipilan Relocation Sites , Brgy. Ipilan | 345877 | _ | _ | 15% | 0 |  | On-going
5 | Proposed Road Concreting - Loleng St. Station 934-74m | Poblacion Dist.II, Brooke's Point, Palawan | 707482.75 | 05/20/2021 | 11/15/2021 | 100% | 674016.47 |  | Completed
6 | Proposed Driveway with RCPC Installation In Front of RHU Bldg. | Rodriguez St. Right Side Poblacion II, Brooke's Point,Palawan | 140751.43 | 2021-06-06 | 2021-02-12 | 100% | 136752 |  | Completed
7 | Proposed Fish Port And Park Development | Poblacion Dist.I, Brooke's Point, Palawan | 4000000 | _ | _ | 10% | 2988851.21 |  | On-going
20% COMPONENT OF THE IRA UTILIZATION
As of 0ctober 31, 2021
| Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incurred to Date
8 | Propposed Municipal Land Transportation Terminal Site Dev't. Phase I | Brgy. Pangobilian, Brooke's Point, Palawan | 1000000 | _ | _ | 80% | 0 |  | On-Going
| TOTAL |  | 12794111.18 |  |  |  | 9673210.14